## ScoringInfo
HSU ITS Project Scoring Rubric Information
The criteria listed below are used to calculate a weighted project score in the Project Scoring Worksheet.
Criteria | Condition (Select best one only) | Weight | Points Assigned
VALUE TO THE UNIVERSITY |  | 29%
1. Is this project required or mandated? |  | 10% |  |  |  | 50 | 50
| Chancellor's Office, legal or collective bargaining requirement |  | 5
| Required to sustain University operations |  | 4
| Required to reduce risk OR to maintain significant funding |  | 3
| Required to reduce institutional cost |  | 1
| Not required |  | 0
2. Does this project support HSU's strategic objectives for IT Project Prioritization? |  | 8% |  |  |  | 40 | 40
| Project meets multiple objectives |  | 5
| Single objective with high priority |  | 3
| Single objective without high priority |  | 1
| No objective supported |  | -2
3. Is the project an urgent need for the University? |  | 4% |  |  |  | 20 | 20
| Urgent for University |  | 5
| Pressing need of the University |  | 4
| Urgent for college or department |  | 3
| Pressing need for College or Department |  | 2
| Not urgent |  | 0
4. What is the impact to the proposed technology system? |  | 4% |  |  |  | 20 | 20
| Replacement (including new systems) |  | 5
| Major or moderate change (including upgrades) |  | 3
| Minimal or no change |  | 1
5. Is there a positive return on investment? |  | 3% |  |  |  | 15 | 15
| Will pay for itself and generate cash or savings for the University |  | 5
| Implemented to avoid cash expenditure |  | 3
| No financial benefit |  | 0
| Non-recoverable cost |  | -2
VALUE TO THE CUSTOMER |  | 25%
6. What are the consequences of doing nothing? |  | 5% |  |  |  | 25 | 25
| Direct significant negative consequences to university or the public, unable to conduct basic services or transactions |  | 5
| Failure to resolve customer service complaints or requests |  | 3
| Loss of opportunity for improved service delivery or efficiency |  | 1
7. How are business rules and/or processes impacted? |  | 5% |  |  |  | 25 | 25
| Significant positive changes |  | 5
| Moderate changes |  | 3
| Insignificant or no change |  | 1
| Significant negative changes |  | -2
8. Does it improve the ability of users to perform tasks? |  | 8% |  |  |  | 40 | 40
| Improves efficiency to the users |  | 5
| No change to users ability to perform tasks |  | 0
| Increases time for users to perform tasks |  | -2
9. What users will be impacted or benefit? |  | 5% |  |  |  | 25 | 0
| More than one division |  | 5
| One division OR More than one department / college |  | 3
| One department / college |  | 1
10. How much job training is necessary? |  | 2% |  |  |  | 10 | 10
| Minimal or none |  | 5
| Moderate |  | 3
| Extensive and substantial |  | 1
PROJECT READINESS |  | 17%
11. Has a project scope been defined? |  | 8% |  |  |  | 40 | 40
| Project scope is well defined, documented and agreed to |  | 5
| A high level scope has been documented |  | 3
| Project scope is undefined or unclear |  | -2
12. Is there available funding for the project? |  | 9% |  |  |  | 45 | 45
| Budget exists (or project has no hard costs) |  | 5
| Partial budget exists |  | 3
| No budget exists |  | -2
TECHNOLOGY SYSTEM RISK |  | 29%
13. What is the effect on IT staffing or technology systems? |  | 4% |  |  |  | 20 | 20
| Staff time saved / system retired |  | 5
| No impact on systems support or staffing |  | 0
| Additional staff / systems needed for support |  | -2
14. What is the state of the current system? |  | 10% |  |  |  | 50 | 50
| Completely inadequate / end of life OR system doesn't exist |  | 5
| Functioning, but close to end of life |  | 3
| Functioning (including manual / paper processes), but could be better |  | 1
15. What type of data is involved? |  | 5% |  |  |  | 25 | 25
| Mission critical and/or processes Level 1 confidential data |  | 5
| Secondary restoration and processes Level 2 protected university information |  | 3
| Processes Level 3 public data |  | 1
16. What is the technology maturity, complexity, and the University's experience with it? |  | 5% |  |  |  | 25 | 25
| Proven, standard technology with sufficient University experience |  | 5
| Proven, standard technology with no University experience OR Emerging/new/complex technology with sufficient University experience |  | 3
| Emerging/new/complex technology AND/OR little or no University experience |  | 1
17. What is the success track record of the vendor and University resources? |  | 5% |  |  |  | 25 | 25
| Uses documented & repeatable processes for tracking status, problems and change |  | 5
| Good success but without structure for repeatability |  | 3
| Inability to mitigate risk |  | 1 | #REF! | 95 | 500
| TOTAL WEIGHT | 100%

## ScoringRubric
Project Name:
Click on the individual Score Assigned field to see the values and use the drop down list to select the value.
| Criteria | Weight | Score Assigned | Weighted Score
VALUE TO THE UNIVERSITY |  | 29%
| 1. Is this project required or mandated? | 10% |  | 0 | Required | 5 | 4 | 3 | 3 | 1 | 0
| 2. Does this project support HSU's strategic objectives for IT Project Prioritization? | 8% |  | 0 | 7-HSU Initiatives | 5 | 3 | 1 | -2
| 3. Is the project an urgent need for the University? | 4% |  | 0 | 10-Urgency | 5 | 4 | 3 | 2 | 0
| 4. What is the impact to the proposed technology system? | 4% |  | 0 | System Impact | 5 | 3 | 1
| 5. Is there a positive return on investment? | 3% |  | 0 | 9-ROI | 5 | 3 | 0 | -2
VALUE TO THE CUSTOMER |  | 25%
| 6. What are the consequences of doing nothing? | 5% |  | 0 | 2-Consequences | 5 | 3 | 1
| 7. How are business rules and/or processes impacted? | 5% |  | 0 | Impact | 5 | 3 | 1 | -2
| 8. Does it improve the ability of users to perform tasks? | 8% |  | 0 | 4-Perform | 5 | 0 | -2
| 9. What users will be impacted or benefit? | 5% |  | 0 | Impact | 5 | 3 | 1
| 10. How much job training is necessary? | 2% |  | 0 | Training | 5 | 3 | 1
PROJECT READINESS |  | 17%
| 11. Has a project scope been defined? | 8% |  | 0 | Scope | 5 | 3 | -2
| 12. Is there available funding for the project? | 9% |  | 0 | Funding | 5 | 3 | -2
TECHNOLOGY SYSTEM RISK |  | 29%
| 13. What is the effect on IT staffing or technology systems? | 4% |  | 0 | 3-Effect |  | 5 | 0 | -2
| 14. What is the state of the current system? | 10% |  | 0 | 5-State | 5 | 3 | 1
| 15. What type of data is involved? | 5% |  | 0 | Data Type | 5 | 3 | 1
| 16. What is the technology maturity, complexity, and the University's experience with it? | 5% |  | 0 | Maturity | 5 | 3 | 1
| 17. What is the project success track record of the vendor and University resources? | 5% |  | 0 | Success | 5 | 3 | 1
| Project Value Totals |  | 0 | 0
| Project Value Maximums | 100% | 85 | 500
Project Prioritization Steering Committee Review
Date: |  |  |  |  | Results
General Comments
Resource Comments